Joint UAT Timeline — BRD Module Coverage

Project: Zetapharma Sales Cloud for Pharmaceuticals

Document type: UAT / Validation Schedule (aligned to BRD Modules summary §4 & Module requirements §5)

Period: Sunday 25 October 2026 – Tuesday 3 November 2026  |  Working week: Sun–Thu

Parties: Cloudastick (first-pass) × Zeta Pharma (retest / acceptance)

Reference: Zeta Business Requirements Document (Discovery Draft)

1. Graphical timeline (BRD functionalities in each box)

Figure 1 — Every box lists the BRD functionalities under test that day. Top = Cloudastick first-pass; bottom = Zeta retest of the prior working day’s BRD cluster.

2. Handoff model

Cloudastick first-passes a BRD module cluster each working day. Next working day Zeta retests that same cluster on the same named users, while Cloudastick opens the next cluster. First standup: Mon 26 Oct. Coverage close: Tue 3 Nov.

3. BRD functionalities by wave

Wave A · SFE foundation  |  Sun 25 Oct CS → Mon 26 Oct Zeta

BRD refs: Admin / Commercial Ops (#23), Territory Alignment & Targeting (#17), Users Management (#14), Product Management (#13)

MoSCoW: M

Functionalities shown in the timeline box:

• Admin / Commercial Ops

• Territory Alignment

• Users Management

• Product Management

• Planner Rules / Holidays

• Promo Grid · Bricks

Wave B · Commercial data  |  Mon 26 Oct CS → Tue 27 Oct Zeta

BRD refs: Account Management (#1), Target Governance, Plan Cycle & Rep 360 / KPIs (#21), Distributor Sales Data (#15)

MoSCoW: M

Functionalities shown in the timeline box:

• Account Management

• Target & Master Lists

• Target Governance

• Plan Cycle & KPIs

• Call Target Rules

• Distributor Sales Data

Wave C · Content & setup  |  Tue 27 Oct CS → Wed 28 Oct Zeta

BRD refs: CLM / e-detailing (#18), Ratings Management (#3), LMS (#12), Coaching Management (#11), Meetings Setup (#10), Sample Management (#19)

MoSCoW: M

Functionalities shown in the timeline box:

• CLM / e-detailing

• Ratings Management

• LMS · Quizzes

• Coaching Management

• Meetings Setup

• Sample Logistics

Wave D · Rep core  |  Wed 28 Oct CS → Thu 29 Oct Zeta

BRD refs: Field Experience Home+Planner (#20), Visits / Planner lifecycle (#5), Time Off Territory (#8)

MoSCoW: M

Functionalities shown in the timeline box:

• Field Experience (Home)

• Visits · Planner lifecycle

• Time Off Territory

• AM / PM channel rules

• Overlap validations

• Offline sync (PWA)

Wave E · Rep depth  |  Thu 29 Oct CS → Sun 1 Nov Zeta

BRD refs: Account (#1), Affiliation (#2), Ratings (#3), Call Report, CLM (#18), Samples (#19), Sales Orders (#25), LMS (#12)

MoSCoW: M

Functionalities shown in the timeline box:

• Account Mgmt (HCP/HCO/Rx)

• Affiliation Management

• Call Report shell

• CLM in-visit player

• Sample Management

• Sales Orders · LMS

Wave F · Managers  |  Sun 1 Nov CS → Mon 2 Nov Zeta

BRD refs: Reporting & Dashboards (#22), Coaching (#11), Approvals, Users Management hierarchy scope

MoSCoW: M

Functionalities shown in the timeline box:

• Reporting & Dashboards

• Workforce / Team KPIs

• Coaching Management

• Approvals (TOT/Visit)

• Field Tracking · My Team

• Hierarchy scope

Wave G · Meetings+  |  Mon 2 Nov CS → Tue 3 Nov Zeta

BRD refs: Meetings/Promotional Activities (#10), WhatsApp assist (#9 C), Reporting/MR 360 (#21–22), KAM (5.4.6), Care Coach, Field AI

MoSCoW: M / S / C

Functionalities shown in the timeline box:

• Meetings / Promo Activities

• WhatsApp assist (QR)

• Reporting · MR 360

• KAM Module

• Pharmacy Sales analytics

• Care Coach · Field AI

Wave H · Sign-off  |  Tue 3 Nov both

BRD refs: Closed commercial loop; BRD §9 UAT exit

MoSCoW: M

Functionalities shown in the timeline box:

• Closed commercial loop

• Account→Territory→Plan

• Call Report→Dashboards

• Retest open defects

• Dual-party sign-off

• BRD §9 UAT exit

4. Day-at-a-glance

| Date | Cloudastick (BRD functionalities) | Zeta retest | Lane |
| --- | --- | --- | --- |
| Sun 25 Oct | Admin Ops · Territory · Users · Products · Planner Rules · Promo/Bricks | — | SFE |
| Mon 26 Oct | Accounts · Targets · Governance · Plan Cycle · Call Target Rules · Dist. Sales | Wave A | SFE |
| Tue 27 Oct | CLM · Ratings · LMS · Coaching · Meetings Setup · Sample Logistics | Wave B | SFE |
| Wed 28 Oct | Field Home · Visits/Planner · TOT · AM/PM · Overlaps · Offline PWA | Wave C | Rep |
| Thu 29 Oct | Accounts · Affiliations · Call Report · CLM · Samples · Orders/LMS | Wave D | Rep |
| Fri–Sat | Off | Off | — |
| Sun 1 Nov | Dashboards · Workforce KPIs · Coaching · Approvals · Field Tracking | Wave E | Mgr |
| Mon 2 Nov | Meetings · WhatsApp QR · MR 360 · KAM · Pharmacy Sales · Care Coach/AI | Wave F | Close |
| Tue 3 Nov | Closed loop · defect retest · dual-party sign-off (BRD §9) | Wave G → sign | Close |

5. Suggested named seats

Medical Rep: Abadir Esmat (GIT-I ASSUIT-A). District Manager: Ahmed Magdy (GIT-I DM CAIRO B). SFE: Pharma_Admin + Pharma_SFE_App.

6. Sign-off

| Party | Name | Date | Coverage overall |
| --- | --- | --- | --- |
| Cloudastick |  | 3 Nov 2026 | Pass / Fail / Blocked |
| Zeta Pharma |  | 3 Nov 2026 | Pass / Fail / Blocked |