## Dry-run checklist
Zeta Pharma — Post dry-run validation checklist (22 Oct 2026)
# | Area | Check | How to verify | Pass/Fail | Notes
1 | Users | Active / inactive / total counts show for current filter | Territory Management → Users header
2 | Users | Filter by Title, Territory, Line, BU (server-side) | Pick GIT-I; count matches roster seats
3 | Users | No 200-row / pharma username cap | Line with >200 people still complete
4 | Users | Field Intelligence Manager visible when Line = Any | Title filter FI
5 | Territories | Filter tree by Business Unit | Pick CHC BU; only CHC + CHC_Sales
6 | Territories | Call rate column on territory rows | Position / district shows Daily_Visit_Rate
7 | Territories | Line shows descendant users without expanding every district | GIT-I Assigned users / rollup
8 | Products | Multi-select bulk remove from Manage Products | Select 3, Remove selected
9 | Hierarchy | Brand Manager seated on line; Group Brand Lead on BU | Roster / Users tab
10 | Hierarchy | CHC_Sales Area Manager has line scope (no National) | Login as code 21; sees whole CHC_Sales
11 | Mirrors | CHC details mirrored to CHC_Sales; GIT to GIT-SALES; CVM sees CHC_Sales set | Product Lines → Manage Products
12 | Login As | Salesforce Login As used; OTP is password reset only | Users → View record / Login As
13 | Territory switch | No permission errors for entitled managers | Switch district / line
14 | Class Engine | Rep edits potential/penetration only; DM edits frequency; class locked for DM | Open Draft cycle
15 | Visits | Out-of-target completed visit does not count until DM Valid | Unplanned visit → check Actuals
16 | Distributors | Zeta Direct upload available; all aliases page past 500 | Distributors Management
17 | Sales | Tender excluded from achievements; public price by month | After post-June file
18 | KPI | Working days after holidays/TOT; double visit target per deck | After KPI PPT arrives
19 | Planner rules | Override by profile / title / user / line | Planner Rules admin
20 | Service requests | Types/subtypes and titles configurable | Admin Console
21 | Data | HCO/HCP wipe+reload only after target lists + backup | Do not run until Zeta confirms