## Issues
Date | Reporter | Title | Line / BU | Screen / Module | Steps to reproduce | Expected | Actual | Severity (Blocker/High/Med/Low) | Screenshot link | Status | Owner | Resolution notes
2026-10-21 | Dry run | SFE | All | Territory Management → Users | Open Users tab, filter by Line GIT-I | All users on the line | Only ~200 usernames with 'pharma'; many missing | Blocker |  | Open | Cloudastick
2026-10-21 | Dry run | SFE | All | Territory Management → Users | Filter by Title Field Intelligence Manager | FI users listed | FI missing / blank line hides them | High |  | Open | Cloudastick
2026-10-21 | Dry run | SFE | All | Territory Management → Products | Remove several products from a line | Multi-select bulk remove | One remove at a time | High |  | Open | Cloudastick
2026-10-21 | Dry run | Rep / Manager | Any | Territory Switcher / Class Engine | Switch territory or open classification | Works for entitled roles | Permission / field errors reported in room | Blocker |  | Open | Cloudastick

## How to use
SFE / field bug log — Oct 21 dry run onward
Add one row per issue. Attach screenshots to the shared drive and paste the link.
Severity: Blocker = blocks training; High = wrong data or missing users; Med = workaround exists; Low = polish.
Return this file to Cloudastick before Cairo rep training.